## Daily Work Log & Tasks
SwiftPLM Consulting Services — Master Daily Work Log & Tasks Database
Central transaction database for team daily activities, billable client hours, training upskilling, and standup tracking. Compatible with CS Support Dashboard (cs.swiftplm.com).
TOTAL LOGGED |  | PROJECT (BILLABLE) |  | TRAINING (UPSKILLING) |  | INTERNAL / ADMIN |  | ACTIVE TEAM MEMBERS |  | STATUS SUMMARY
13 Consultants
LOG ID | DATE | ENGINEER | CATEGORY | CLIENT / DOMAIN | TASK DESCRIPTION | HOURS | STATUS | PRIORITY | STANDUP NOTES / BLOCKERS / DETAILS | CREATED BY (UPN) | CREATED AT
LOG-1001 | 2026-09-09 | Viswateja Balla | Project (Billable) | CWG | Windchill 13.1 Upgrade script validation and custom action testing | 4.5 | In Progress | High | Testing listeners on Dev2 environment; coordinating with CWG PLM team | vballa@swiftplm.com | 2026-09-09 17:07:07
LOG-1002 | 2026-09-09 | Viswateja Balla | Training (Upskilling) | Windchill Customization & APIs | Research and prototype ThingWorx REST API integration with Windchill WRS | 2.5 | Completed | Medium | Completed Swagger test suite and sample JSON payload builders | vballa@swiftplm.com | 2026-09-09 17:07:07
LOG-1003 | 2026-09-09 | Anagha Shete | Project (Billable) | bioMérieux | CAD drawing consolidation template debugging and PDF conversion test | 5 | Completed | High | Resolved LibreOffice conversion spacing and header layout issue | ashete@swiftplm.com | 2026-09-09 17:07:07
LOG-1004 | 2026-09-09 | Babalu Shinde | Training (Upskilling) | Windchill Administration & Config | Windchill Lifecycle workflows, ACL security profiles & OIR autonumbering lab | 6 | Completed | Medium | Completed hands-on configuration for multi-organization lifecycle templates | bshinde@swiftplm.com | 2026-09-09 17:07:07
LOG-1005 | 2026-09-09 | Anil Kumar | Project (Billable) | Detex | Consulting Support Log task migration and review for project #260503 | 4 | Completed | High | All 10 support tasks verified with customer stakeholder | akumar@swiftplm.com | 2026-09-09 17:07:07
LOG-1006 | 2026-09-09 | Anil Kumar | Internal / Admin | Daily Standup / Team Sync | Team Daily Standup & technical peer review for ArvinSango cycle 2 | 1.5 | Completed | Low | Discussed SUM formula offset and sheet validation | akumar@swiftplm.com | 2026-09-09 17:07:07
LOG-1007 | 2026-09-09 | Sanket Jadhav | Project (Billable) | Amcor | Amcor cycle 2 data validation and Windchill worker agent health check | 5.5 | Completed | Medium | Worker queues verified; no publishing backlogs | sjadhav@swiftplm.com | 2026-09-09 17:07:07
LOG-1008 | 2026-09-09 | Prajyot Jagtap | Project (Billable) | CWG | Custom Change Notice save-as delegation API testing and debugging | 6 | In Progress | High | Root cause identified: unhandled null pointer during CAD attribute copy | pjagtap@swiftplm.com | 2026-09-09 17:07:07
LOG-1009 | 2026-09-09 | Pranav | Training (Upskilling) | Creo CAD Automation & Toolkit | PTC Creo Toolkit and automated drawing generation pipeline study | 5 | In Progress | Medium | Reviewing C++/Java bindings for Creo drawing title block updates | pranav@swiftplm.com | 2026-09-09 17:07:07
LOG-1010 | 2026-09-09 | Nandu B | Project (Billable) | CWG | UAT testing test case review and drawing code sync validation | 4.5 | In Progress | High | Validating test cases with Viswateja post connection to CWG environment | nandub@swiftplm.com | 2026-09-09 17:07:07
LOG-1011 | 2026-09-09 | Gargee J | Training (Upskilling) | Windchill Customization & APIs | Windchill WRS REST services endpoint exploration and OAuth authentication test | 6 | Completed | Medium | Validated Swagger schema for parts, BOM, and change notices | gj@swiftplm.com | 2026-09-09 17:07:07
LOG-1012 | 2026-09-09 | Balaji Gapat | Project (Billable) | Rev Group | Rev Group onboarding, cycle #260504 sheet verification and initial ticket queue setup | 5 | Completed | Medium | SharePoint cs_config.json sync confirmed | bgapat@swiftplm.com | 2026-09-09 17:07:07
LOG-1013 | 2026-09-08 | Ayyappa Kamuju | Training (Upskilling) | Azure Cloud & SWA Architecture | Azure Static Web Apps deployment pipeline and Oryx build analysis | 6.5 | Completed | Medium | Documented StaticSitesClient.exe standalone deployment steps | akamuju@swiftplm.com | 2026-09-09 17:07:07
LOG-1014 | 2026-09-08 | Sumit Wani | Project (Billable) | ArvinSango | ArvinSango billing cycle 2 task execution and CAD publish error monitoring | 5 | Completed | Medium | Monitored CAD workers during large assembly check-in | swani@swiftplm.com | 2026-09-09 17:07:07
LOG-1015 | 2026-09-08 | Surender Kumar | Project (Billable) | bioMérieux | bioMérieux consulting support log review and drawing metadata extraction script | 5.5 | Completed | Medium | Confirmed end dates and dynamic active cycle labels | skumar@swiftplm.com | 2026-09-09 17:07:07

## Standup & Team Summary
SwiftPLM Consulting Services — Team Daily Standup & Workload Summary
Live executive summary per engineer: 8-hour target tracking, billable project allocation, and training effort.
ENGINEER | DAILY GOAL (HRS) | TOTAL LOGGED (HRS) | PROJECT (BILLABLE) | TRAINING (UPSKILLING) | INTERNAL / ADMIN | GOAL STATUS | UTILIZATION %
Anagha Shete | 8
Anil Kumar | 8
Ayyappa Kamuju | 8
Babalu Shinde | 8
Balaji Gapat | 8
Gargee J | 8
Nandu B | 8
Prajyot Jagtap | 8
Pranav | 8
Sanket Jadhav | 8
Sumit Wani | 8
Surender Kumar | 8
Viswateja Balla | 8
TEAM TOTAL

## Reference_Tables
Engineers (13) | Categories | Clients & Domains | Statuses | Priorities
Anagha Shete | Project (Billable) | CWG | Completed | Critical
Anil Kumar | Training (Upskilling) | Detex | In Progress | High
Ayyappa Kamuju | Internal / Admin | ArvinSango | Blocked | Medium
Babalu Shinde | PM | Amcor | Pending Review | Low
Balaji Gapat |  | bioMérieux
Gargee J |  | Rev Group
Nandu B |  | Windchill Customization & APIs
Prajyot Jagtap |  | Windchill Administration & Config
Pranav |  | ThingWorx IIoT & Integrations
Sanket Jadhav |  | Creo CAD Automation & Toolkit
Sumit Wani |  | Java & Spring Boot Development
Surender Kumar |  | Azure Cloud & SWA Architecture
Viswateja Balla |  | Python & Scripting Automation
PLM Architecture & Migration
Daily Standup / Team Sync
Technical Peer Review
Internal SwiftPLM
Other...